## index
MyTGuide Project Plan
Index
Version 1.0
2017-09-15
MyTGuide
Author(s)
Pedro Portugal Nº 69405 Henrique Lourenço Nº77459 José Touret Nº 78215
Description
FreeTime intends to launch a new innovative service in the tourism sector supported by a digital platform, MyTGuide which consists in two apps, MyTGuidePartner app and MyTGuideClient app, and a website, MyTGuide.com. Clients will be able to search, book and evaluate tours and Partners will be able to offer their guide services.

## int.charter
Back to Index
MyTGuide
Integration :: Project Charter
Project Identification
Project Name | MyTGuide | Project # | 15
Project Sponsor | Alberto da Silva | Project Manager | Henrique Lourenço
Application Domain | Other | Type | System Development
Project Constraints
Start Date | First week of 2018 | End Date | First week of July
Price/Cost | 200000 | Other
Purpose: What? (scope statement) | A product that allows tourists to book and get information about tours and evaluate them and another that allows guides to offer their services (tours).
Purpose: Why? | To innovate and simplify the tourists tours services while speeding up the whole booking and offering process.
Business Benefits
BB_1 | To have a easy to use, scalable and secure online platform.
BB_2 | Smooth operation of the business, namely in what concerns its main processes.
BB_3 | Proper integration with external systems, namely with the Bank Gateway and its ERP/Accounting systems.
BB_4 | Efficient use of involving human resources.
BB_5 | Invoicing over 200 k€, by the end of the first year, regarding this specific new business.
Success Criteria
SC_1 | Project cost under budget limit |  | between € 188,000 and € 212,000
SC_2 | Project concluded on time |  | before third week of July
SC_3 | Number of non-conformities under limit |  | under 10
SC_4 | Time spent correcting non-conformities under limit |  | under 48 hours
SC_5 | Training sessions evaluation over minimum |  | over 3,5
Success Factors
SF_1 | Servers and computers to develop the project
SF_2 | Highly motivated project team
SF_3 | Available users to test the product
SF_4 | FreeTime company's commitment
SF_5 | Optimized scope without goals that do not need to be met
SF_6 | FreeTime and Softhouse good relationship
Project Stakeholders
STK1 | FreeTime Customers |  | Innovative app to search and book tours
STK2 | FreeTime Partners |  | Innovative app to offer tour services
STK3 | FreeTime Company |  | Successful project delivered
STK4 | Sponsor |  | Income from the project
STK5 | DAF - Administrative and Financial Department: |  | Income from the project
STK6 | DMC - Department of Marketing and Customer Support |  | Satisfied customers
STK7 | DAP - Partner Support Department |  | Satisfied partners
STK8 | DSI - IT Department |  | System well implemented
Project Manager | Signature:
Name: Henrique Afonso Ferreira da Silva Lourenço
Date: 12 April 2017
Note on A14: GPI: linked with business benefits

## wbs.dictionary
Back to Index
MyTGuide
Scope :: Work Breakdown Structure Dictionary
Project
Sub-Project, Phase
Workpackage
WP Id (*) | Name (*) | WP Description | Milestone
WP_1 | Start-up | Project start-up | Mi_1 | Initial project plan validated
WP_2 | Plan and Control | Plan to develop and manage the project | Mi_2
WP_3 | Closure | Finish the project | Mi_3 | Project concluded successfuly
WP_4 | Requirement specification | Specify project requirements | Mi_4 | Creation and validation of the System Requirements Specification Document
WP_5 | Information architecture | Choose products architecture | Mi_5 | Creation and validation of the System Architecture and Design Document
WP_6 | Front-end Specification | Specify the front-end design | Mi_6 | Creation and validation of the System Architecture and Design Document
WP_7 | MyTGuide Partner app | MyTGuide app to be accessed by partners | Mi_7 | Finished development of MyTGuide Partner app source code
WP_8 | MyTGuide Client app | MyTGuide app to be accessed by clients | Mi_8 | Finished development ofMyTGuide Client app source code
WP_9 | MyTGuide.com | MyTGuide website to be accessed by both partners and clients | Mi_9 | Finished development of MyTGuide.com source code
WP_10 | Integration Tests | Creating tests to the final product | Mi_10 | Finished all creation of test for the MyTGuide system
WP_11 | Acceptance Tests | Testing the final product to check if every requirement is met | Mi_11 | Successful validation of the project
WP_12 | Usability Tests | Evaluating the product by testing it with real users | Mi_12 | User satisfaction above threshold
WP_13 | Support | Supply the client with availability to solve any problems with the product | Mi_14
WP_14 | Warranty | Guarantee that the product will work as intended for the defined time | Mi_15

## scope.deliverables
Back to Index
MyTGuide
Scope :: Deliverables Table
Id (*) | Name (*) | Type (*) | Work Package | Description
D_1 | MyTGuide system | Software Application | WP_7,WP_8,WP_9 | Deployed applications with all the respective functionalities implemented
D_2 | Source code | Documentation | WP_7,WP_8,WP_9 | Code of MyTGuide apllications an the respective documentation
D_3 | Project related reports | Documentation | WP_1,WP_2,WP_3 | All the reports created in the project lifetime
D_4 | System Requirements Specification | Documentation | WP_4 | Document with all requirements and use cases of the system
D_5 | System Architecture and Design | Documentation | WP_5, WP_6 | Document with all architecture and design choices of the system
D_6 | User Guides and additional training materials | Documentation | Mi_13 | All documentation regarding how to work with the system
D_7 | System Tests Specification | Documentation | WP_10 | All tests used on the system

## .config
Back to Index
#REF!
General Configuration
Project Types
Type: | System Development | System Deployment | System Maintenance | Training | Research | Sales & Marketing | Other
ApplicationDomain | Public Sector | Education | Health | Telecoms | Energy & Utilities | Finance & Banks | Other
ProgressState | Not Plan | Plan | On Design | On Develop | On Test | On Deploy | Concluded
ProjectNationalityType | National | International
Glossary Types
Type: | Stakeholder | Entity | Architectural | Actor | Stakeholder_Actor | Stakeholder_Entity | Stakeholder_Actor_Entity
POS (part-of-speech): | Adjective | Adverb | Noun | Verb
Synset:
Term Relation Type: | Antonym | Hypernym | Synonym
Business_Trainer
Stakeholder Types
Type: | Organization | Business Unit | Team | Person | External System | Other
Category: | Business | Business_Customer | Business_Customer_Sponsor | Business_Customer_Other | Business_User_Direct | Business_User_Indirect | Business_Government | Business_Regulatory | Business_Advisor | Business_System
DependsOn Type | is-part-of
Other Types
Boolean | Yes | No
Scope
WorkComponentType | Project | Sub-Project | Phase | Workpackage | Other
TaskType | Project | Sub-Project | Phase | Workpackage | Milestone | Activity | Other
TaskQualityType | QA | QC | Other
DeliverableType | Documentation | Software Application | Software Infrastructure | Hardware | Network Infrastructure | Other
DeliverableStatus | Not Submitted | In Review | Approved | Rejected | Other
MilestoneType | Main | Minor | Other
MilestoneStatus | Not Reached | Reached
Quality
TaskQualityType | QP | QA | QC
Organization & Stakeholder Types
OrganizationType | Customer | Performing | Sub-Contractor | Other
Type: | Organization | Business Unit | Team | Person | External System | Other
Category: | Project Owner | Project Sponsor | Project Manager | Team Leader | Team Member | Functional Manager | Other
DependsOn Type | is-part-of
ResponsabilityType | X | P | D | d | C | A | I | T
Communication Types
MeetingType | is-part-of X: Technical; is-part-of P: Management; is-part-of D: Steering; is-part-of d: Other
CommunicationMedium | is-part-of X: Face-To-Face; is-part-of P: Conference Call; is-part-of D: Email; is-part-of d: Other
CommunicationFrequency | Once | Weekly | Bi-Weekly | Monthly | As-Needed
Issues Types
IssueType | Bug | Enhancement | Change | Problem | Task | Other
IssueStatus | Opened | Approved | Rejected | On Progress | Canceled | Closed
Priority | Very High | High | Medium | Low | Very Low
Costs
CostType | HRs | Travels | Equipments | Materials | Services | Suppliers | General | Capital | Other | Total
ResourceType | is-part-of X: HR; is-part-of P: Equipment; is-part-of D: Other
UnitMeasure | Hourly | Daily | Monthly | Yearly | Other
Risk | bar: is-part-of X to is-part-of I
RiskType | Scope | Scheduling | Resource | Technology | Other
RiskSWOTCategory | is-part-of X: Strength; is-part-of P: Weakness; is-part-of D: Opportunity; is-part-of d: Threat
RiskProbability | Very High | High | Medium | Low | Very Low
RiskConsequence | Very High | High | Medium | Low | Very Low
RiskImpact | Very High | High | Medium | Low | Very Low
RiskStrategyResponse | Avoid | Transfer | Mitigate | Accept | Exploit | Enhance
RiskStatus | Identified | Assessed | Planned | On Process | Closed | Not Occurred | Rejected
Identified - a risk that has been identified, but has not yet been analyzed / assessed yet
Assessed - an identified risk which currently has no risk response plan
Planned - An identified risk with a risk response plan.
In-Process - A risk where the risk response is being executed
Closed - A risk that occurred and is transfered to an issue or the risk was solved/avioded
Not occurred - A risk that was identified but that did not occur
Rejected - Created and kept for tracking pruposes but considered not to be used yet
Time Types
TaskDependencyType | is-part-of X: Finish-To-Start; is-part-of P: Start-To-Start; is-part-of D: Finish-To-Finish; is-part-of d: Start-To-Finish