## index
MyTGuide Project Plan
Index
Version 1.0
2017-11-17
MyTGuide
Group 15
Pedro Portugal Nº 69405 Henrique Lourenço Nº77459 José Touret Nº 78215
Description
FreeTime intends to launch a new innovative service in the tourism sector supported by a digital platform, MyTGuide which consists in two apps, MyTGuidePartner app and MyTGuideClient app, and a website, MyTGuide.com. Clients will be able to search, book and evaluate tours and Partners will be able to offer their guide services.

## int.charter
MyTGuide
Integration :: Project Charter
Project Identification
Project Name | MyTGuide | Project # | 15
Project Sponsor | Alberto da Silva | Project Manager | Henrique Lourenço
Application Domain | Other | Type | System Development
Project Constraints
Start Date | First week of 2018 | End Date | First week of July of 2018
Price/Cost | 200000 | Other
Purpose: What? (scope statement) | To create a product with 3 platforms, one app which will allow tourists to book and get information about tours and in the end evaluate them, another app which will allow tourist guides to offer their services (guides) and a website which will allow both parts to access their respective module
Purpose: Why? | The reason for this project is to create an innovative product which will allow the tourists to look up tours and book them fast and easily and will allow buides to easily offer their services to a big number of tourists
Business Benefits
BB_1 | To have a easy to use, scalable and secure online platform.
BB_2 | Smooth operation of the business, namely in what concerns its main processes.
BB_3 | Proper integration with external systems, namely with the Bank Gateway and its ERP/Accounting systems.
BB_4 | Efficient use of involving human resources.
BB_5 | Invoicing over 200 k€, by the end of the first year, regarding this specific new business.
Success Criteria
SC_1 | Project cost under budget limit |  | between € 188,000 and € 212,000
SC_2 | Project concluded on time |  | before third week of July
SC_3 | Number of non-conformities under limit |  | under 10
SC_4 | Time spent correcting non-conformities under limit |  | under 48 hours
SC_5 | Training sessions evaluation over minimum |  | over 3,5
Success Factors
SF_1 | Equipment provided and installed by SoftwareHouse
SF_2 | Highly motivated project team
SF_3 | Available users to test the product
SF_4 | Optimized project scope
Project Stakeholders
STK1 | FreeTime Customers |  | Innovative app to search and book tours
STK2 | FreeTime Partners |  | Innovative app to offer tour services
STK3 | FreeTime Company |  | Successful project delivered
STK4 | Sponsor |  | Income from the project
STK5 | DAF - Administrative and Financial Department: |  | Project concluded within budget
STK6 | DMC - Department of Marketing and Customer Support |  | Satisfied customers
STK7 | DAP - Partner Support Department |  | Satisfied partners
STK8 | DSI - IT Department |  | System well implemented
Project Manager | Signature:
Name: Henrique Afonso Ferreira da Silva Lourenço
Date: 12 April 2017
Note on A13: GPI: linked with business benefits

## wbs.dictionary
MyTGuide
Scope :: Work Breakdown Structure Dictionary
Project
Sub-Project, Phase
Workpackage
WP Id (*) | Name (*) | WP Description | Milestone
MyTGuide
Project Management
WP_1 | Start-up | Project start-up | Mi_1 | Initial project plan approved
WP_2 | Plan and Control | Plan to develop and manage the project | Mi_2 | Project successfully deployed
WP_3 | Closure | Finish the project | Mi_3 | Project successfuly concluded
System requirements
WP_4 | Requirement specification | Specify System requirements | Mi_4 | System Requirements Specification Document approved
WP_5 | Information architecture | Specify System architecture | Mi_5 | System Architecture and Design Document approved
WP_6 | Tests Specification | Specify the project tests | Mi_6 | System Tests Specification Document approved
Mobile app Software development
WP_7 | MApp Sprint 1 | Mapp development Sprint | Mi_7 | MApp Sprint 1 concluded
WP_8 | MApp Sprint 2 | Mapp development Sprint | Mi_8 | MApp Sprint 2 concluded
WP_9 | MApp Sprint 3 | Mapp development Sprint | Mi_9 | MApp Sprint 3 concluded
WP_10 | MApp Sprint 4 | Mapp development Sprint | Mi_10 | MApp Sprint 4 concluded
WP_11 | MApp Sprint 5 | Mapp development Sprint | Mi_11 | MApp Sprint 5 concluded
Core and Web app Software development
WP_12 | WApp Sprint 1 | Wapp development Sprint | Mi_12 | WApp Sprint 1 concluded
WP_13 | WApp Sprint 2 | Wapp development Sprint | Mi_13 | WApp Sprint 2 concluded
WP_14 | WApp Sprint 3 | Wapp development Sprint | Mi_14 | WApp Sprint 3 concluded
WP_15 | WApp Sprint 4 | Wapp development Sprint | Mi_15 | WApp Sprint 4 concluded
WP_16 | WApp Sprint 5 | Wapp development Sprint | Mi_16 | WApp Sprint 5 concluded
Transition
WP_17 | Acceptance Tests | Testing the final product to check if every requirement is met | Mi_17 | Project successfully approved
WP_18 | Deployment | Deploy the product in the Market | Mi_18 | Project successfully deployed
WP_19 | Training | Train the FreeTime's team to manage with the system | Mi_19 | User Guide approved Free Time's training completed
Operation
WP_20 | Support | Supply the client with availability to solve any problems with the product | Mi_20 | Planned technical support time period ended

## scope.deliverables
MyTGuide
Scope :: Deliverables Table
Id (*) | Name (*) | Type (*) | Work Package | Description
D_1 | MyTGuide system | Software Application | WP_18 | Deployed applications with all the respective functionalities implemented
D_2 | Source code | Documentation | WP_7 to WP_16 | Code of MyTGuide applications and the respective documentation
D_3 | Project related reports | Documentation | WP_1,WP_2,WP_3 | All the reports created in the project lifetime
D_4 | System Requirements Specification | Documentation | WP_4 | Document with all requirements and use cases of the system
D_5 | System Architecture and Design | Documentation | WP_5 | Document with all architecture and design choices of the system
D_6 | User Guides and additional training materials | Documentation | WP_19 | All documentation regarding how to work with the system
D_7 | System Tests Specification | Documentation | WP_6 | All tests used on the system

## resources.obs
MyTGuide
Organization Resources :: Organization Breakdown Structure
Groups
Individuals
Id (*) | Name (*) | Type (*) | Role (*) | Organization (*) | PartOf | ReportTo | Description
Stk_01 | FreeTime | Organization | Other | Customer |  |  | Customer company
Stk_02 | FreeTime's team | Team | Other | Customer | Stk_01 |  | FreeTime's team
Stk_03 | Software House | Organization | Other | Performing |  |  | Developing company
Stk_04 | SoftwareHouse's team | Team | Other | Performing | Stk_03 |  | SoftwareHouse's team
Stk_05 | Alberto da Silva | Person | Project Sponsor | Performing | Stk_04 |  | SoftwareHouse's partner
Stk_06 | Henrique Lourenço | Person | Project Manager | Performing | Stk_04 | Stk_18 | SoftwareHouse's team manager
Stk_07 | Miguel Touret | Person | Team Leader; Scrum Master | Performing | Stk_04 | Stk_06 | SoftwareHouse's mobile app team leader
Stk_08 | MApp team member #1 | Person | Team Member | Performing | Stk_04 | Stk_07 | SoftwareHouse's mobile app team member
Stk_09 | MApp team member #2 | Person | Team Member | Performing | Stk_04 | Stk_07 | SoftwareHouse's mobile app team member
Stk_10 | Pedro Portugal | Person | Team Leader; Scrum Master | Performing | Stk_04 | Stk_06 | SoftwareHouse's core and web team leader
Stk_11 | WApp team member #3 | Person | Team Member | Performing | Stk_04 | Stk_10 | SoftwareHouse's core and web app team member
Stk_12 | WApp team member #4 | Person | Team Member | Performing | Stk_04 | Stk_10 | SoftwareHouse's core and web app team member
Stk_13 | DAF K-user | Person | Team Member | Customer | Stk_02 | Stk_20 | Administrative and Financial Department's K-user
Stk_14 | DMC K-user | Person | Team Member | Customer | Stk_02 | Stk_20 | Department of Marketing and Customer Support's K-user
Stk_15 | DAP Director | Person | Project Owner | Customer | Stk_02 |  | Partner Support Department's director
Stk_16 | DSI Deputy Director | Person | Project Manager | Customer | Stk_02 | Stk_17 | IT Department's deputy director
Stk_17 | DSI-UO SysAdmin | Person | Team Leader | Customer | Stk_02 | Stk_18 | DSI-UO's System administrator
Stk_18 | DAP K-user | Person | Functional Manager; Product Owner | Customer | Stk_02 | Stk_17 | Partner Support Department's K-user
Stk_19 | DSI-UAQ technical engineer #1 | Person | Team Leader | Customer | Stk_02 | Stk_18 | DSI-UAQ technical engineer responsible for ERP integration and system tests
Stk_20 | DSI-UAQ technical engineer #2 | Person | Team Member | Customer | Stk_02 | Stk_21 | DSI-UAQ technical engineer responsible for ERP integration and system tests
Stk_21 | Client's External Users | Person | Team Member | Sub-Contractor | Stk_10 | Stk_20 | 2 external users as representatives from Clients group
Stk_22 | Partner's External Users | Person | Team Member | Sub-Contractor | Stk_11 | Stk_20 | 2 external users as representatives from Partners group

## resources.ram
MyTGuide
Organization Resources :: Responsability Assignment Matrix
WP-ID | WP-Name | SoftwareHouse Project Manager | Mapp Team Leader | Wapp TeamLeader | Project Owner | FreeTime Project Manager | DAP K-user (Functional Manager)
T_1 | Start-up | X/P |  |  | D | d |  | T_1
T_2 | Plan and Control | X/P |  |  | D | d |  | T_2
T_3 | Closure | X/P |  |  | D | d |  | T_3
T_4 | Requirement specification | P | X |  | D | d | C | T_4
T_5 | Information architecture | P |  | X | D | d |  | T_5
T_6 | Tests Specification | P |  | X | D | d | C | T_6
T_7 | MApp Sprint 1 | P | X |  |  |  |  | T_7
T_8 | MApp Sprint 2 | P | X |  |  |  |  | T_8
T_9 | MApp Sprint 3 | P | X |  |  |  |  | T_9
T_10 | MApp Sprint 4 | P | X |  |  |  |  | T_10
T_11 | MApp Sprint 5 | P | X |  |  |  |  | T_11
T_12 | WApp Sprint 1 | P |  | X |  |  |  | T_12
T_13 | WApp Sprint 2 | P |  | X |  |  |  | T_13
T_14 | WApp Sprint 3 | P |  | X |  |  |  | T_14
T_15 | WApp Sprint 4 | P |  | X |  |  |  | T_15
T_16 | WApp Sprint 5 | P |  | X |  |  |  | T_16
T_17 | Acceptance Tests | P |  |  | D | d | X | T_17
T_18 | Deployment | P |  | X |  |  |  | T_18
T_19 | Training | P | X |  |  | I |  | T_19
T_20 | Support | P |  | X |  |  |  | T_20

## comm.flow
MyTGuide
Communication :: Communication Flows
What |  |  |  | Who |  | When |  | How
Id (*) | Deliverable / Other Document |  | Type (*) | Owner (From) | Audience (To) | Frequency | When | Medium | Format | Description
| Id (*) | Name
CF_1 | D_2 | Source code | Technical | Henrique Lourenço (PM) | DSI Deputy Director (PM) | Once |  | Email | .cpp | Delivery of deliverable D_2
CF_2 | D_3 | Code documentation | Technical | Henrique Lourenço (PM) | DSI Deputy Director (PM) | Once |  | Email | PDF | Delivery of deliverable D_3
CF_3 | D_4 | Project related reports | Technical | Henrique Lourenço (PM) | DSI Deputy Director (PM) | Once |  | Email | PDF | Delivery of deliverable D_4
CF_4 | D_5 | System Requirements Specification | Technical | Henrique Lourenço (PM) | DSI Deputy Director (PM) | Once |  | Email | PDF | Delivery of deliverable D_5
CF_5 | D_6 | System Architecture and Design | Technical | Henrique Lourenço (PM) | DSI Deputy Director (PM) | Once |  | Email | PDF | Delivery of deliverable D_6
CF_6 | D_7 | User Guides and additional training materials | Technical | Henrique Lourenço (PM) | DSI Deputy Director (PM) | Once |  | Email | PDF | Delivery of deliverable D_7
CF_7 | D_8 | System Tests Specification | Technical | Henrique Lourenço (PM) | DSI Deputy Director (PM) | Once |  | Email | PDF | Delivery of deliverable D_8
CF_8 | D_9 | Mobile app Software Sprint report | Management | Miguel Touret (Mapp Team Leader) | Henrique Lourenço | Bi-Weekly | Every Friday | Email | PDF | Report of mobile app development status
CF_9 | D_10 | Core and Web app Software Sprint report | Management | Pedro Portugal (Wapp Team Leader) | Henrique Lourenço | Bi-Weekly | Every Friday | Email | PDF | Report of core and web app development status
CF_10 | D_11 | MyTGuide Status report | Management | Henrique Lourenço (PM) | DSI Deputy Director (PM) | Monthly | Last working day of the month | Email | PDF | Report of MyTGuide status
CF_11 | D_12 | Status report | Management | DSI Deputy Director (PM) | DAP Director (Owner) | As-Needed |  | Email | PDF | Report of MyTGuide status

## comm.meet
MyTGuide
Communication :: Meetings
Id (*) | Description | Type (*) | Frequency | Owner | Audience | Deliverable(s) if any | Description
CM_1 | Mapp Sprint Planning | Technical | Monthly | Scrum Master | Product Owner, Mapp Team
CM_2 | Wapp Sprint Planning | Technical | Monthly | Scrum Master | Product Owner, Wapp Team
CM_3 | Mapp Sprint Review | Technical | Monthly | Mapp Team | Product Owner, Scrum Master
CM_4 | Wapp Sprint Review | Technical | Monthly | Wapp Team | Product Owner, Scrum Master
CM_5 | Mapp Sprint Retrospective | Technical | Monthly | Scrum Master | Mapp Team
CM_6 | Wapp Sprint Retrospective | Technical | Monthly | Scrum Master | Wapp Team
CM_7 | Mapp Daily Scrum | Steering | Daily | Scrum Master | Mapp Team
CM_8 | Wapp Daily Scrum | Steering | Daily | Scrum Master | Wapp Team

## risk.id + assessement
MyTGuide
Risks :: Risk Register: Identification
Identification |  |  |  | Assessment |  |  | Probability Level
Id (*) | Name (*) | Description | Assumptions | Probability Level | Consequence Level | Impact Level | Very High | [6 empty] | Impact Level
R_1 | Problem in Bank Gateway Integration | Difficulty in project integration with the current Bank Gateway |  | High | High | High | High |  | R_7 |  | R_1, R_2 |  |  | High
R_2 | Problem in ERP Integration | Difficulty in project integration with the current ERP |  | High | High | High | Medium |  |  | R_4 | R_3 |  |  | Medium
R_3 | Incorrect project time estimation | Incorrect estimation of project time | The project may take longer than expected (or less) | Medium | High | Medium | Low |  |  | R_5, R_6 |  |  |  | Low
R_4 | Incorrect project cost estimation | Incorrect estimation of project cost | The project budget was not enough | Medium | Medium | Medium | Very Low |  |  |  | R_
R_5 | Technical training | Trouble in training DSI department’s technical engineers |  | Low | Medium | Low |  | Very Low | Low | Medium | High | Very High | Consequence Level
R_6 | K-users training | Trouble in training K-users from the DMC and DAP departments |  | Low | Medium | Low
R_7 | Current available data extraction | Trouble in training K-users from the DMC and DAP departments | Some data extracted from the Excel sheets might be incomplete or wrong | High | Low | Low
R_8 | Team members leaving | Team members might leave the current project or be unavailable for long period of time, be it for health or professional reason |  | Very Low | High | Low

## risk.treatment
Back to Index
MyTGuide
Risks :: Risk Register: Treatment
Identification |  | Treatment |  | Owner
Id (*) | Name (*) | Type | Description
R_1 | Problem in Bank Gateway Integration | Acceptance | accept the extra time/cost on the integration | SoftwareHouse PM
R_2 | Problem in ERP Integration | Transfer | Assume responsibility of the problems with integration | DSI-UO SysAdmin
R_3 | Incorrect project time estimation | Mitigation | Schedule review and control meetings to ensure that the time requirements are being met. Re-adjust the plan if needed. | SoftwareHouse PM
R_4 | Incorrect project cost estimation | Mitigation | Schedule review and control meetings to ensure that the cost requirements are being met. Re-adjust the plan if needed. | SoftwareHouse PM
R_5 | Technical training | Transfer | Assume responsibility of the problems with training | SoftwareHouse PM
R_6 | K-users training | Transfer | Assume responsibility of the problems with training | SoftwareHouse PM
R_7 | Current available data extraction | Mitigation | Double check the excel sheets and correct the wrong data if necessary. | SoftwareHouse PM
R_8 | Team members leaving | Acceptance | Ensure a smooth transition in the replacement of the team member. | SoftwareHouse PM

## .config
Back to Index
#REF!
General Configuration
Project Types
Type: | System Development | System Deployment | System Maintenance | Training | Research | Sales & Marketing | Other
ApplicationDomain | Public Sector | Education | Health | Telecoms | Energy & Utilities | Finance & Banks | Other
ProgressState | Not Plan | Plan | On Design | On Develop | On Test | On Deploy | Concluded
ProjectNationalityType | National | International
Glossary Types
Type: | Stakeholder | Entity | Architectural | Actor | Stakeholder_Actor | Stakeholder_Entity | Stakeholder_Actor_Entity
POS (part-of-speech): | Adjective | Adverb | Noun | Verb
Synset:
Term Relation Type: | Antonym | Hypernym | Synonym
Business_Trainer
Stakeholder Types
Type: | Organization | Business Unit | Team | Person | External System | Other
Category: | Business | Business_Customer | Business_Customer_Sponsor | Business_Customer_Other | Business_User_Direct | Business_User_Indirect | Business_Government | Business_Regulatory | Business_Advisor | Business_System
DependsOn Type | is-part-of
Other Types
Boolean | Yes | No
Scope
WorkComponentType | Project | Sub-Project | Phase | Workpackage | Other
TaskType | Project | Sub-Project | Phase | Workpackage | Milestone | Activity | Other
TaskQualityType | QA | QC | Other
DeliverableType | Documentation | Software Application | Software Infrastructure | Hardware | Network Infrastructure | Other
DeliverableStatus | Not Submitted | In Review | Approved | Rejected | Other
MilestoneType | Main | Minor | Other
MilestoneStatus | Not Reached | Reached
Quality
TaskQualityType | QP | QA | QC
Organization & Stakeholder Types
OrganizationType | Customer | Performing | Sub-Contractor | Other
Type: | Organization | Business Unit | Team | Person | External System | Other
Category: | Project Owner | Project Sponsor | Project Manager | Team Leader | Team Member | Functional Manager | Other
DependsOn Type | is-part-of
ResponsabilityType | X | P | D | d | C | A | I | T
Communication Types
MeetingType | is-part-of X: Technical; is-part-of P: Management; is-part-of D: Steering; is-part-of d: Other
CommunicationMedium | is-part-of X: Face-To-Face; is-part-of P: Conference Call; is-part-of D: Email; is-part-of d: Other
CommunicationFrequency | Once | Weekly | Bi-Weekly | Monthly | As-Needed
Issues Types
IssueType | Bug | Enhancement | Change | Problem | Task | Other
IssueStatus | Opened | Approved | Rejected | On Progress | Canceled | Closed
Priority | Very High | High | Medium | Low | Very Low
Costs
CostType | HRs | Travels | Equipments | Materials | Services | Suppliers | General | Capital | Other | Total
ResourceType | is-part-of X: HR; is-part-of P: Equipment; is-part-of D: Other
UnitMeasure | Hourly | Daily | Monthly | Yearly | Other
Risk | bar: is-part-of X to is-part-of I
RiskType | Scope | Scheduling | Resource | Technology | Other
RiskSWOTCategory | is-part-of X: Strength; is-part-of P: Weakness; is-part-of D: Opportunity; is-part-of d: Threat
RiskProbability | Very High | High | Medium | Low | Very Low
RiskConsequence | Very High | High | Medium | Low | Very Low
RiskImpact | Very High | High | Medium | Low | Very Low
RiskStrategyResponse | Avoid | Transfer | Mitigate | Accept | Exploit | Enhance
RiskStatus | Identified | Assessed | Planned | On Process | Closed | Not Occurred | Rejected
Identified - a risk that has been identified, but has not yet been analyzed / assessed yet
Assessed - an identified risk which currently has no risk response plan
Planned - An identified risk with a risk response plan.
In-Process - A risk where the risk response is being executed
Closed - A risk that occurred and is transfered to an issue or the risk was solved/avioded
Not occurred - A risk that was identified but that did not occur
Rejected - Created and kept for tracking pruposes but considered not to be used yet
Time Types
TaskDependencyType | is-part-of X: Finish-To-Start; is-part-of P: Start-To-Start; is-part-of D: Finish-To-Finish; is-part-of d: Start-To-Finish